## WORKDAY worked examples
Adding working days to a date
Worked Examples
Without the WORKDAY function - end dates are incorrect because of weekends
Start date | Task | Duration | End Date |  | End Date 2
2015-04-22 | Project Kickoff | 1 | 2015-04-23 |  | 2015-04-23
2015-04-23 | Task 1 | 2 | 2015-04-25 |  | 2015-04-27
2015-04-25 | Task 2 | 15 | 2015-05-10 |  | 2015-05-15
2015-05-10 | Task 3 | 5 | 2015-05-15 |  | 2015-05-15
2015-05-15 | Task 4 | 3 | 2015-05-18 |  | 2015-05-20
2015-05-18 | Project end | 0 | 2015-05-18 |  | 2015-05-18
With the WORKDAY function - end dates are now correct and account for weekends
Start date | Task | Duration | End Date
2015-04-22 | Project Kickoff | 1 | 2015-04-23 | =WORKDAY(A14,C14)
2015-04-23 | Task 1 | 2 | 2015-04-27 | =WORKDAY(A15,C15)
2015-04-27 | Task 2 | 15 | 2015-05-18 | =WORKDAY(A16,C16)
2015-05-18 | Task 3 | 5 | 2015-05-25 | =WORKDAY(A17,C17)
2015-05-25 | Task 4 | 3 | 2015-05-28 | =WORKDAY(A18,C18)
2015-05-28 | Project end | 0 | 2015-05-28 | =WORKDAY(A19,C19)
With the WORKDAY function and taking account of holidays during the project.
Start date | Task | Duration | End Date
2017-06-22 | Project Kickoff | 1 | 2017-06-23 | =WORKDAY(A23,C23,$A$32:$A$43)
2017-06-23 | Task 1 | 2 | 2017-06-27 | =WORKDAY(A24,C24,$A$32:$A$43)
2017-06-27 | Task 2 | 15 | 2017-07-19 | =WORKDAY(A25,C25,$A$32:$A$43)
2017-07-19 | Task 3 | 5 | 2017-07-26 | =WORKDAY(A26,C26,$A$32:$A$43)
2017-07-26 | Task 4 | 3 | 2017-07-31 | =WORKDAY(A27,C27,$A$32:$A$43)
2017-07-31 | Project end | 0 | 2017-07-31 | =WORKDAY(A28,C28,$A$32:$A$43)
US Holiday dates for 2017, for use with the WORKDAY function
2017-01-01 | New Year's Day
2017-01-02 | New Year's Day (observed)
2017-01-16 | Martin Luther King Day
2017-02-20 | Presidents' Day*
2017-05-29 | Memorial Day
2017-07-04 | Independence Day
2017-09-04 | Labor Day
2017-10-09 | Columbus Day
2017-11-10 | Veterans Day (observed)
2017-11-11 | Veterans Day
2017-11-23 | Thanksgiving Day
2017-11-25 | Christmas Day
Formulas:
End Date = [Start date]+[Duration]
End Date = WORKDAY([Start date],[Duration])
End Date 2 = WORKDAY([Start date],[Duration])
Start date = [End Date, row above]